## Meeting with Mentor
STT | Date | Time | Member | Address | Content disscuss | Có/Không Mentor
1 | 23/8/2018 | 8h30 AM | Trường,Trúc,Oanh, Mentor | 03 Quang Trung | Deploy schedule and discuss topic selection | Yes
Select the process for the project
Choose software that supports teamwork
2 | 31/8/2018 | 9h30 AM | Trúc,Trường,Nghĩa,Mentor | 03 Quang Trung | Used scum process and trello teamwork organization, github Writing Proposal | Yes
Viết Proposal
3 | 2018-07-09 | 9h15 AM | Team, Mentor | 03 Quang Trung | brainstorm ideas , create user story, product backlog | Yes
4 | 20/9/2018 | 8h00 AM | Team +Mentor | 03 Quang Trung | Writing script for game explain word | Yes
Determine the constraints on the game
Identify game techniques
5 | 28/9/2018 | 9h15 AM | Team,Mentor | 03 Quang Trung | Report each person's work | Yes
Divide the group into two pairs, one pair of documents, one pair of code
6 | 2018-10-11 | 8h00 AM | Trúc,Trường,Nghĩa,Mentor | 03 Quang Trung | how to structure the data, divided into streams of data to catch logic | Yes
7 | 17/11/2018 | 8h00 AM | Trường,Trúc,Oanh, Mentor | 3 Quang Trung | review and edit user story, product backlog, architecture | Yes
8 | 25/11/2018 | 8h00 AM | Team, Mentor | 3 Quang Trung | Review all documentation and source code, documentation and documentation | Yes
9 | 2018-01-12 | 8h00 AM | Trúc,Oanh,Nghĩa, Mentor | 3 Quang Trung | Review document, instructions to edit database document | Yes

## Team Meeting
STT | Date | Time | Member | Location | Content
| 2018-08-20 | 7:00 | Team | Phan Thanh Library | Meeting , get ideas about project
| 2018-09-01 | 15:00 | Team | Phan Thanh Library | Làm tài liệu Proposal.
| 2018-09-08 | 7:00 | Team | Phan Thanh Library | Update user story, plan
| 2018-09-13 | 15:00 | Team | Phan Thanh Library | Edit User Story, Create Product backlog
| 2018-09-21 | 8:00 | Team | Phan Thanh Library | Complete Proposal ver 1.0
| 2018-10-02 | 9:00 | Team | Phan Thanh Library | Write Sprint backlog, Design Database
| 2018-10-06 | 7:30 | Team | Phan Thanh Library | Devide Design User interface
| 2018-10-14 | 7:30 | Team | Phan Thanh Library | Complete UI , Devide task for sprint
| 2018-10-16 | 15:00 | Team | Phan Thanh Library | Create sprint 1, code function sprint 1.
| 2018-10-19 | 8:00 | Team | Phan Thanh Library | Code Funtion Sprint 1, Check Interface, Update Document
| 2018-10-20 | 8:00 | Team | Phan Thanh Library | Fix Bug, Review test case
| 2018-10-26 | 14:00 | Team | Phan Thanh Library | Design database sprint 2 • Discussion about: ◦ What did you learn in Sprint 1? ◦ How to get better results in Sprint 2?
| 2018-10-30 | 14:00 | Team | Phan Thanh Library | Fix bug catalog
| 2018-11-05 | 14:00 | Team | Phan Thanh Library | Code &fix bug
| 2018-11-06 | 14:00 | Team | Phan Thanh Library | Review document for midterm report
| 2018-11-12 | 14:00 | Team | Phan Thanh Library | Code and fix bug, update test case
| 2018-11-19 | 14:00 | Team | Phan Thanh Library | Disscuss problem and change solution , update document
| 2018-11-23 | 14:00 | Team | Phan Thanh Library | Disscuss how are the projects being implemented?
| 2018-11-27 | 15:00 | Team | Phan Thanh Library | Review all documentation and source code
| 2018-12-03 | 14:00 | Team | Phan Thanh Library | Review the documents to prepare the final report