## Estimate
No | Product Backlog Item | Task | Assign to | Total | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-17
1 |  | Design user interface of Home page | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Code front-end for Home page | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | As an User I want to login and logout to the system So that I can use my account Can I login with facebook | Design user interface of login-logout | Trần Nguyễn Hữu Nghĩa | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Design a Database for login-logout | Trần Nguyễn Hữu Nghĩa | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Code front-end for Login-logout | Đỗ Văn Trường | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Code back-end for Login-logout | Đỗ Văn Trường | 6 | 0 | 1 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | As an User I want to remember my password So that I did need to login in the next times | Design user interface of remember password | Trần Nguyễn Hữu Nghĩa | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Design a Database for remember password | Đỗ Văn Trường | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  | Code front-end for remember password | Trần Nguyễn Hữu Nghĩa | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Code back-end for remember password | Đỗ Văn Trường | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | As a User I want to have a chat form So that I can explain and answer with my teamate | Design user interface of chat form (explainer) | Đỗ Văn Trường | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  | Code front-end for Chat form | Trần Nguyễn Hữu Nghĩa | 8 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Code back-end for Chat form | Trần Nguyễn Hữu Nghĩa | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | As an User I want to connect with other players quickly and do not spend too much time on the connection. | Design user interface waiting page(waiting to connect with other player) | Đỗ Văn Trường | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  | Design a Database for waiting page(waiting to connect with other player) | Trần Nguyễn Hữu Nghĩa | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 |  | Code front-end for waiting page | Đỗ Văn Trường | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  | Code back-end for waiting page | Trần Nguyễn Hữu Nghĩa | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
18 | As a User I want to time a game not too long, too much time to complete a game Can i play the game in two minutes | Design user interface of play time | Trần Nguyễn Hữu Nghĩa | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
19 |  | Code front-end for playtime | Đỗ Văn Trường | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
20 |  | Code back-end for playtime | Trần Nguyễn Hữu Nghĩa | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
21 |  | Design Test Case for Homepage | Đỗ Văn Trường | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
22 |  | Design Test Case for Login-Logout | Trần Nguyễn Hữu Nghĩa | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
23 |  | Design Test Case for remember password | Đỗ Văn Trường | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
24 |  | Design Test Case for waiting page | Trần Nguyễn Hữu Nghĩa | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
25 |  | Design Test Case for Chat form (explainer) | Trần Nguyễn Hữu Nghĩa | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
26 |  | Design Test Case for Chat form (ansswer) | Đỗ Văn Trường | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
27 |  | Design Test Case for playtime | Trần Nguyễn Hữu Nghĩa | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
28 |  | Implement Test Case | Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
29 |  | Fix bugs and Report | Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
30 |  | Retest | Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
31 |  | Closing | Team | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  | total | 76 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4

## Actual
No | Product Backlog Item | Task | Assign to | Total | Actual | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-17
1 |  | Design user interface of Home page | Trần Nguyễn Hữu Nghĩa | 1 | bar: 2018-09-28
2 |  | Code front-end for Home page | Trần Nguyễn Hữu Nghĩa | 2
3 | As an User I want to login and logout to the system So that I can use my account Can I login with facebook | Design user interface of login-logout | Trần Nguyễn Hữu Nghĩa | 1
4 |  | Design a Database for login-logout | Trần Nguyễn Hữu Nghĩa | 1
5 |  | Code front-end for Login-logout | Đỗ Văn Trường | 1
6 |  | Code back-end for Login-logout | Đỗ Văn Trường | 1
7 | As an User I want to remember my password So that I did need to login in the next times | Design user interface of remember password | Trần Nguyễn Hữu Nghĩa
8 |  | Design a Database for remember password | Đỗ Văn Trường
9 |  | Code front-end for remember password | Trần Nguyễn Hữu Nghĩa
10 |  | Code back-end for remember password | Đỗ Văn Trường
11 | As a User I want to have a chat form So that I can explain and answer with my teamate | Design user interface of chat form (explainer) | Đỗ Văn Trường
12 |  | Code front-end for Chat form | Trần Nguyễn Hữu Nghĩa
13 |  | Code back-end for Chat form | Trần Nguyễn Hữu Nghĩa
14 | As an User I want to connect with other players quickly and do not spend too much time on the connection. | Design user interface waiting page(waiting to connect with other player) | Đỗ Văn Trường
15 |  | Design a Database for waiting page(waiting to connect with other player) | Trần Nguyễn Hữu Nghĩa
16 |  | Code front-end for waiting page | Đỗ Văn Trường
17 |  | Code back-end for waiting page | Trần Nguyễn Hữu Nghĩa
18 | As a User I want to time a game not too long, too much time to complete a game Can i play the game in two minutes | Design user interface of play time | Trần Nguyễn Hữu Nghĩa
19 |  | Code back-end for playtime | Đỗ Văn Trường
20 |  | Code back-end for playtime | Trần Nguyễn Hữu Nghĩa
21 |  | Design Test Case for Homepage | Đỗ Văn Trường
22 |  | Design Test Case for Login-Logout | Trần Nguyễn Hữu Nghĩa
23 |  | Design Test Case for remember password | Đỗ Văn Trường
24 |  | Design Test Case for waiting page | Trần Nguyễn Hữu Nghĩa
25 |  | Design Test Case for Chat form (explainer) | Trần Nguyễn Hữu Nghĩa
26 |  | Design Test Case for Chat form (ansswer) | Đỗ Văn Trường
27 |  | Design Test Case for playtime | Trần Nguyễn Hữu Nghĩa
28 |  | Implement Test Case | Team
29 |  | Fix bugs and Report | Team
30 |  | Retest | Team
31 |  | Closing | Team
Estimate
[5 empty] | Actual | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0