## Estimate
No | Product Backlog Item | Task | Assign to | Total | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-17
1 |  | Design user interface of Home page | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Code front-end for Home page | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | As an User I want to login and logout to the system So that I can use my account Can I login with facebook | Design user interface of login-logout | Trần Nguyễn Hữu Nghĩa | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Design a Database for login-logout | Trần Nguyễn Hữu Nghĩa | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Code front-end for Login-logout | Đỗ Văn Trường | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Code back-end for Login-logout | Đỗ Văn Trường | 6 | 6 | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | As an User I want to remember my password So that I did need to login in the next times | Design user interface of remember password | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Design a Database for remember password | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  | Code front-end for remember password | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Code back-end for remember password | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | As a User I want to have a chat form So that I can explain and answer with my teamate | Design user interface of chat form (explainer) | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  | Code front-end for Chat form | Trần Nguyễn Hữu Nghĩa | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Code back-end for Chat form | Trần Nguyễn Hữu Nghĩa | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | As an User I want to connect with other players quickly and do not spend too much time on the connection. | Design user interface waiting page(waiting to connect with other player) | Đỗ Văn Trường | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  | Design a Database for waiting page(waiting to connect with other player) | Trần Nguyễn Hữu Nghĩa | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 |  | Code front-end for waiting page | Đỗ Văn Trường | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  | Code back-end for waiting page | Trần Nguyễn Hữu Nghĩa | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0
18 | As a User I want to time a game not too long, too much time to complete a game Can i play the game in two minutes | Design user interface of play time | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
19 |  | Code front-end for playtime | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
20 |  | Code back-end for playtime | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
21 |  | Design Test Case for Homepage | Đỗ Văn Trường | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
22 |  | Design Test Case for Login-Logout | Trần Nguyễn Hữu Nghĩa | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
23 |  | Design Test Case for remember password | Đỗ Văn Trường | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
24 |  | Design Test Case for waiting page | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
25 |  | Design Test Case for Chat form (explainer) | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
26 |  | Design Test Case for Chat form (ansswer) | Đỗ Văn Trường | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
27 |  | Design Test Case for playtime | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
28 |  | Implement Test Case | Team | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
29 |  | Fix bugs and Report | Team | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
30 |  | Retest | Team | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
31 |  | Closing | Team | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  | total | 76 | 76 | 72 | 68 | 64 | 60 | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0

## Actual
No | Product Backlog Item | Task | Assign to | Total | Actual | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-17
1 |  | Design user interface of Home page | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Code front-end for Home page | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | As an User I want to login and logout to the system So that I can use my account Can I login with facebook | Design user interface of login-logout | Trần Nguyễn Hữu Nghĩa | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Design a Database for login-logout | Trần Nguyễn Hữu Nghĩa | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
5 |  | Code front-end for Login-logout | Đỗ Văn Trường | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Code back-end for Login-logout | Đỗ Văn Trường | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
7 | As an User I want to remember my password So that I did need to login in the next times | Design user interface of remember password | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
8 |  | Design a Database for remember password | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
9 |  | Code front-end for remember password | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
10 |  | Code back-end for remember password | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
11 | As a User I want to have a chat form So that I can explain and answer with my teamate | Design user interface of chat form (explainer) | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
12 |  | Code front-end for Chat form | Trần Nguyễn Hữu Nghĩa | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
13 |  | Code back-end for Chat form | Trần Nguyễn Hữu Nghĩa | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
14 | As an User I want to connect with other players quickly and do not spend too much time on the connection. | Design user interface waiting page(waiting to connect with other player) | Đỗ Văn Trường | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
15 |  | Design a Database for waiting page(waiting to connect with other player) | Trần Nguyễn Hữu Nghĩa | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
16 |  | Code front-end for waiting page | Đỗ Văn Trường | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
17 |  | Code back-end for waiting page | Trần Nguyễn Hữu Nghĩa | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
18 | As a User I want to time a game not too long, too much time to complete a game Can i play the game in two minutes | Design user interface of play time | Trần Nguyễn Hữu Nghĩa | 1 | 1 | bar: 2018-09-28 to 2018-10-17
19 |  | Code back-end for playtime | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
20 |  | Code back-end for playtime | Trần Nguyễn Hữu Nghĩa | 1 | 1 | bar: 2018-09-28 to 2018-10-17
21 |  | Design Test Case for Homepage | Đỗ Văn Trường | 1 | 1 | bar: 2018-09-28 to 2018-10-17
22 |  | Design Test Case for Login-Logout | Trần Nguyễn Hữu Nghĩa | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
23 |  | Design Test Case for remember password | Đỗ Văn Trường | 1 | 1 | bar: 2018-09-28 to 2018-10-17
24 |  | Design Test Case for waiting page | Trần Nguyễn Hữu Nghĩa | 1 | 1 | bar: 2018-09-28 to 2018-10-17
25 |  | Design Test Case for Chat form (explainer) | Trần Nguyễn Hữu Nghĩa | 1 | 1 | bar: 2018-09-28 to 2018-10-17
26 |  | Design Test Case for Chat form (ansswer) | Đỗ Văn Trường | 1 | 1 | bar: 2018-09-28 to 2018-10-17
27 |  | Design Test Case for playtime | Trần Nguyễn Hữu Nghĩa | 1 | 1 | bar: 2018-09-28 to 2018-10-17
28 |  | Implement Test Case | Team | 1 | 1 | bar: 2018-09-28 to 2018-10-17
29 |  | Fix bugs and Report | Team | 1 | 1 | bar: 2018-09-28 to 2018-10-17
30 |  | Retest | Team | 1 | 1 | bar: 2018-09-28 to 2018-10-17
31 |  | Closing | Team | 1 | 1 | bar: 2018-09-28 to 2018-10-17
[5 empty] | Estimate | 76 | 72 | 68 | 64 | 60 | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
[5 empty] | Actual | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 76 | 71 | 71 | 71 | 71 | 63 | 63 | 63