## Estimate
No | Product Backlog Item | Task | Assign to | Total | 2018-10-20 | 2018-10-21 | 2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-25 | 2018-10-26 | 2018-10-27 | 2018-10-28 | 2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08
1 | Login-Logout | Code back-end for Login-logout | Trần Nguyễn Hữu Nghĩa | 5 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | As a User I want to have a chat form So that I can explain and answer with my teamate | Code front-end for Chat form | Trần Nguyễn Hữu Nghĩa | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | Code back-end for Chat form | Đỗ Văn Trường | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | As an User I want to connect with other players quickly and do not spend too much time on the connection. | Design a Database for waiting page(waiting to connect with other player) | Đỗ Văn Trường | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Code back-end for waiting page | Trần Nguyễn Hữu Nghĩa | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | As a User I want to time a game not too long, too much time to complete a game Can i play the game in two minutes | Design user interface of play time | Đỗ Văn Trường | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Code front-end for playtime | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Code back-end for playtime | Đỗ Văn Trường | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | As an User I want to choose words to explain to my teamate So that I can know what words to explain Can I see it below chat form | Design user interface of words to explain | Đỗ Văn Trường | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Design a Database for Choose words to explain | Trần Nguyễn Hữu Nghĩa | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | Code front-end of choose words to explain | Trần Nguyễn Hữu Nghĩa | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  | Code back-end of choose words to explain | Đỗ Văn Trường | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | As a User I want to change vocabulary when my teamate can’t answer that vocabulary So that I can save time to get more point Can I see another words below to change | Design user interface of change words story | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Code front-end of Change words | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  | Code back-end of Change words | Trần Nguyễn Hữu Nghĩa | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | As an User I want to know what is type of vocabulary (noun, adjective, verb) So that when I was explained I can easily guess that words Can I see type of vocabulary beside suggest square | Design user interface of type of vocabulary | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  | Design a Database for Type of vocabulary | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  | Code front-end of Type of vocabulary | Trần Nguyễn Hữu Nghĩa | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 |  | Code back-end of Type of vocabulary | Đỗ Văn Trường | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
20 | As a User I want to suggest the character of words I need to guess So that I can more easily guess Can I See each cell square show for each character | Design user interface of Suggest character of words | Đỗ Văn Trường | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | Design a Database for Suggest character of words | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
22 |  | Code front-end of Suggest character of words | Trần Nguyễn Hữu Nghĩa | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
23 |  | Code back-end of Suggest character of words | Trần Nguyễn Hữu Nghĩa | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
24 | As a User I want to count my point if I have correct answers So that I can compare my team point with enemy point | Design user interface point | Đỗ Văn Trường | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
25 |  | Design a Database for Point | Đỗ Văn Trường | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
26 |  | Code front-end of Point | Trần Nguyễn Hữu Nghĩa | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
27 |  | Code back-end of Point | Trần Nguyễn Hữu Nghĩa | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3.5 | 0 | 0 | 0
28 | As a User I want to be notification when I have correct answers So that I can know that my answer is correct | Design user interface notification answer correct | Đỗ Văn Trường | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
29 |  | Code front-end of notification answer correct | Trần Nguyễn Hữu Nghĩa | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
30 |  | Code back-end of notification answer correct | Trần Nguyễn Hữu Nghĩa | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0
31 |  | Design Test Case for Choose word explain | Trần Nguyễn Hữu Nghĩa | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
32 |  | Design Test Case for change word | Đỗ Văn Trường | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
33 |  | Design Test Case for Type of vocabulary | Trần Nguyễn Hữu Nghĩa | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
34 |  | Design Test Case for Suggest character of words | Trần Nguyễn Hữu Nghĩa | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
35 |  | Design Test Case for point | Đỗ Văn Trường | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
36 |  | Design Test Case for notification answer correct | Đỗ Văn Trường | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
37 |  | Implement Test Case | Team | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 |  | Fix bugs and Report | Team | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 |  | Retest | Team | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 |  | Closing | Team | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | total | 76 | 76 | 72 | 68 | 64 | 60 | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0

## Actual
No | Product Backlog Item | Task | Assign to | Total | Actual | 2018-10-20 | 2018-10-21 | 2018-10-22 | 2018-10-23 | 2018-10-24 | 2018-10-25 | 2018-10-26 | 2018-10-27 | 2018-10-28 | 2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08
1 | Login-Logout | Code back-end for Login-logout | Trần Nguyễn Hữu Nghĩa | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | As a User I want to have a chat form So that I can explain and answer with my teamate | Code front-end for Chat form | Trần Nguyễn Hữu Nghĩa | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | Code back-end for Chat form | Đỗ Văn Trường | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | As an User I want to connect with other players quickly and do not spend too much time on the connection. | Design a Database for waiting page(waiting to connect with other player) | Đỗ Văn Trường | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Code back-end for waiting page | Trần Nguyễn Hữu Nghĩa | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | As a User I want to time a game not too long, too much time to complete a game Can i play the game in two minutes | Design user interface of play time | Đỗ Văn Trường | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Code front-end for playtime | Trần Nguyễn Hữu Nghĩa | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Code back-end for playtime | Đỗ Văn Trường | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | As an User I want to choose words to explain to my teamate So that I can know what words to explain Can I see it below chat form | Design user interface of words to explain | Đỗ Văn Trường | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Design a Database for Choose words to explain | Trần Nguyễn Hữu Nghĩa | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 |  | Code front-end of choose words to explain | Trần Nguyễn Hữu Nghĩa | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  | Code back-end of choose words to explain | Đỗ Văn Trường | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | As a User I want to change vocabulary when my teamate can’t answer that vocabulary So that I can save time to get more point Can I see another words below to change | Design user interface of change words story | Trần Nguyễn Hữu Nghĩa | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Code front-end of Change words | Đỗ Văn Trường | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  | Code back-end of Change words | Trần Nguyễn Hữu Nghĩa | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | As an User I want to know what is type of vocabulary (noun, adjective, verb) So that when I was explained I can easily guess that words Can I see type of vocabulary beside suggest square | Design user interface of type of vocabulary | Trần Nguyễn Hữu Nghĩa | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  | Design a Database for Type of vocabulary | Đỗ Văn Trường | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  | Code front-end of Type of vocabulary | Trần Nguyễn Hữu Nghĩa | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 |  | Code back-end of Type of vocabulary | Đỗ Văn Trường | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | As a User I want to suggest the character of words I need to guess So that I can more easily guess Can I See each cell square show for each character | Design user interface of Suggest character of words | Đỗ Văn Trường | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | Design a Database for Suggest character of words | Trần Nguyễn Hữu Nghĩa | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 |  | Code front-end of Suggest character of words | Trần Nguyễn Hữu Nghĩa | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 |  | Code back-end of Suggest character of words | Trần Nguyễn Hữu Nghĩa | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | As a User I want to count my point if I have correct answers So that I can compare my team point with enemy point | Design user interface point | Đỗ Văn Trường | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 |  | Design a Database for Point | Đỗ Văn Trường | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 |  | Code front-end of Point | Trần Nguyễn Hữu Nghĩa | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 |  | Code back-end of Point | Trần Nguyễn Hữu Nghĩa | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | As a User I want to be notification when I have correct answers So that I can know that my answer is correct | Design user interface notification answer correct | Đỗ Văn Trường | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 |  | Code front-end of notification answer correct | Trần Nguyễn Hữu Nghĩa | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 |  | Code back-end of notification answer correct | Trần Nguyễn Hữu Nghĩa | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 |  | Design Test Case for Choose word explain | Trần Nguyễn Hữu Nghĩa | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 |  | Design Test Case for change word | Đỗ Văn Trường | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 |  | Design Test Case for Type of vocabulary | Trần Nguyễn Hữu Nghĩa | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 |  | Design Test Case for Suggest character of words | Trần Nguyễn Hữu Nghĩa | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 |  | Design Test Case for point | Đỗ Văn Trường | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 |  | Design Test Case for notification answer correct | Đỗ Văn Trường | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 |  | Implement Test Case | Team | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 |  | Fix bugs and Report | Team | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 |  | Retest | Team | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 |  | Closing | Team | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Estimate | 76 | 72 | 68 | 64 | 60 | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
|  |  |  | 76 | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0