## Sheet1
No | Product Backlog Item | Task | Assign to | Total | Actual | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-17
1 | Home Page | Design user interface of Home page | Trần Nguyễn Hữu Nghĩa
2 |  | Code front-end for Home page | Trần Nguyễn Hữu Nghĩa
3 |  | Code back-end for Home page | Đỗ Văn Trường
4 | As an User I want to login and logout to the system So that I can use my account Can I login with facebook | Design user interface of login-logout | Trần Nguyễn Hữu Nghĩa
5 |  | Design a Database for login-logout | Trần Nguyễn Hữu Nghĩa
6 |  | Code front-end for Login-logout | Đỗ Văn Trường
7 |  | Code back-end for Login-logout | Đỗ Văn Trường
8 | As an User I want to remember my password So that I did need to login in the next times | Design user interface of remember password | Trần Nguyễn Hữu Nghĩa
9 |  | Design a Database for remember password | Đỗ Văn Trường
10 |  | Code front-end for remember password | Trần Nguyễn Hữu Nghĩa
11 |  | Code back-end for remember password | Đỗ Văn Trường
12 | As a User I want to have a chat form So that I can explain and answer with my teamate | Design user interface of chat form (explainer) | Đỗ Văn Trường
13 |  | Code front-end for Chat form | Trần Nguyễn Hữu Nghĩa
14 |  | Code back-end for Chat form | Trần Nguyễn Hữu Nghĩa
15 | As an User I want to connect with other players quickly and do not spend too much time on the connection. | Design user interface waiting page(waiting to connect with other player) | Đỗ Văn Trường
16 |  | Design a Database for waiting page(waiting to connect with other player) | Trần Nguyễn Hữu Nghĩa
17 |  | Code front-end for waiting page | Đỗ Văn Trường
18 |  | Code back-end for waiting page | Trần Nguyễn Hữu Nghĩa
19 | As a User I want to time a game not too long, too much time to complete a game Can i play the game in two minutes | Design user interface of play time | Trần Nguyễn Hữu Nghĩa
20 |  | Code back-end for playtime | Đỗ Văn Trường
21 |  | Code back-end for playtime | Trần Nguyễn Hữu Nghĩa
22 |  | Design Test Case for Homepage | Đỗ Văn Trường
23 |  | Design Test Case for Login-Logout | Trần Nguyễn Hữu Nghĩa
24 |  | Design Test Case for remember password | Đỗ Văn Trường
25 |  | Design Test Case for waiting page | Trần Nguyễn Hữu Nghĩa
26 |  | Design Test Case for Chat form (explainer) | Trần Nguyễn Hữu Nghĩa
27 |  | Design Test Case for Chat form (ansswer) | Đỗ Văn Trường
28 |  | Design Test Case for playtime | Trần Nguyễn Hữu Nghĩa
29 |  | Implement Test Case | Team
30 |  | Fix bugs and Report | Team
31 |  | Retest | Team
32 |  | Closing | Team
Estimate
[5 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0