## Estimate
No | Product Backlog Item | Task | Assign to | Total | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-17
1 |  | Design user interface of Home page | Tran Nguyen Huu Nghia | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Code front-end for Home page | Tran Nguyen Huu Nghia | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | Design Test Case for Homepage | Doan Nu Thuc Oanh | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Test for Homepage | Doan Nu Thuc Oanh | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | As an User I want to login and logout to the system So that I can use my account Can I login with facebook | Design user interface of login-logout | Tran Nguyen Huu Nghia | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Design a Database for login-logout | Tran Nguyen Huu Nghia | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | Code front-end for Login-logout | Do Van Truong | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Code back-end for Login-logout | Do Van Truong | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  | Design Test Case for Login-Logout | Dinh Tran Anh Truc | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Test for Login-Logout | Dinh Tran Anh Truc | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | As an User I want to remember my password So that I did need to login in the next times | Design user interface of remember password | Tran Nguyen Huu Nghia | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  | Design a Database for remember password | Do Van Truong | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  | Code front-end for remember password | Tran Nguyen Huu Nghia | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  | Code back-end for remember password | Do Van Truong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  | Design Test Case for remember password | Doan Nu Thuc Oanh | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 |  | Test for remember password | Doan Nu Thuc Oanh | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | As a User I want to have a chat form So that I can explain and answer with my teamate | Design user interface of chat form (explainer) | Do Van Truong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  | Code front-end for Chat form | Tran Nguyen Huu Nghia | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 |  | Code back-end for Chat form | Tran Nguyen Huu Nghia | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | Design Test Case for Chat form (explainer) | Dinh Tran Anh Truc | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | Test for Chat Form | Dinh Tran Anh Truc | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | As an User I want to connect with other players quickly and do not spend too much time on the connection. | Design user interface waiting page(waiting to connect with other player) | Do Van Truong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 |  | Design a Database for waiting page(waiting to connect with other player) | Tran Nguyen Huu Nghia | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 |  | Code front-end for waiting page | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 |  | Code back-end for waiting page | Tran Nguyen Huu Nghia | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 12 | 8 | 4 | 0 | 0 | 0 | 0
26 |  | Design Test Case for waiting page | Doan Nu Thuc Oanh | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
27 |  | Test for Waiting page | Doan Nu Thuc Oanh | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
28 | As a User I want to time a game not too long, too much time to complete a game Can i play the game in two minutes | Design user interface of play time | Tran Nguyen Huu Nghia | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
29 |  | Code back-end for playtime | Do Van Truong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0
30 |  | Code back-end for playtime | Tran Nguyen Huu Nghia | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
31 |  | Design Test Case for playtime | Dinh Tran Anh Truc | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
32 |  | Test for Playtime | Dinh Tran Anh Truc | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
33 |  | Implement Test Case | Team | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
34 |  | Fix bugs and Report | Team | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
35 |  | Retest | Team | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
36 |  | Closing | Team | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  | total | 76 | 76 | 72 | 68 | 64 | 60 | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0

## Actual
No | Product Backlog Item | Task | Assign to | Total | Actual | 2018-09-28 | 2018-09-29 | 2018-09-30 | 2018-10-01 | 2018-10-02 | 2018-10-03 | 2018-10-04 | 2018-10-05 | 2018-10-06 | 2018-10-07 | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-17
1 |  | Design user interface of Home page | Tran Nguyen Huu Nghia | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 |  | Code front-end for Home page | Tran Nguyen Huu Nghia | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  | Design Test Case for Homepage | Doan Nu Thuc Oanh | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  | Test for Homepage | Doan Nu Thuc Oanh | 1 | 1 | bar: 2018-09-28 to 2018-10-17
5 | As an User I want to login and logout to the system So that I can use my account Can I login with facebook | Design user interface of login-logout | Tran Nguyen Huu Nghia | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Design a Database for login-logout | Tran Nguyen Huu Nghia | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
7 |  | Code front-end for Login-logout | Do Van Truong | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Code back-end for Login-logout | Do Van Truong | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
9 |  | Design Test Case for Login-Logout | Dinh Tran Anh Truc | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | Test for Login-Logout | Dinh Tran Anh Truc | 1 | 1 | bar: 2018-09-28 to 2018-10-17
11 | As an User I want to remember my password So that I did need to login in the next times | Design user interface of remember password | Tran Nguyen Huu Nghia | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  | Design a Database for remember password | Do Van Truong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
13 |  | Code front-end for remember password | Tran Nguyen Huu Nghia | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
14 |  | Code back-end for remember password | Do Van Truong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
15 |  | Design Test Case for remember password | Doan Nu Thuc Oanh | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 |  | Test for remember password | Doan Nu Thuc Oanh | 1 | 1 | bar: 2018-09-28 to 2018-10-17
17 | As a User I want to have a chat form So that I can explain and answer with my teamate | Design user interface of chat form (explainer) | Do Van Truong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  | Code front-end for Chat form | Tran Nguyen Huu Nghia | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
19 |  | Code back-end for Chat form | Tran Nguyen Huu Nghia | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
20 |  | Design Test Case for Chat form (explainer) | Dinh Tran Anh Truc | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | Test for Chat Form | Dinh Tran Anh Truc | 1 | 1 | bar: 2018-09-28 to 2018-10-17
22 | As an User I want to connect with other players quickly and do not spend too much time on the connection. | Design user interface waiting page(waiting to connect with other player) | Do Van Truong | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 |  | Design a Database for waiting page(waiting to connect with other player) | Tran Nguyen Huu Nghia | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
24 |  | Code front-end for waiting page | Đỗ Văn Trường | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
25 |  | Code back-end for waiting page | Tran Nguyen Huu Nghia | 15 | 15 | 15 | 15 | 15 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
26 |  | Design Test Case for waiting page | Doan Nu Thuc Oanh | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 |  | Tes for Waiting page | Doan Nu Thuc Oanh | 1 | 1 | bar: 2018-09-28 to 2018-10-17
28 | As a User I want to time a game not too long, too much time to complete a game Can i play the game in two minutes | Design user interface of play time | Tran Nguyen Huu Nghia | 1 | 1 | bar: 2018-09-28 to 2018-10-17
29 |  | Code back-end for playtime | Do Van Truong | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
30 |  | Code back-end for playtime | Tran Nguyen Huu Nghia | 1 | 1 | bar: 2018-09-28 to 2018-10-17
31 |  | Design Test Case for playtime | Dinh Tran Anh Truc | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 |  | Test for Playtime | Dinh Tran Anh Truc | 1 | 1 | bar: 2018-09-28 to 2018-10-17
33 |  | Implement Test Case | Team | 1 | 1 | bar: 2018-09-28 to 2018-10-17
34 |  | Fix bugs and Report | Team | 1 | 1 | bar: 2018-09-28 to 2018-10-17
35 |  | Retest | Team | 1 | 1 | bar: 2018-09-28 to 2018-10-17
36 |  | Closing | Team | 1 | 1 | bar: 2018-09-28 to 2018-10-17
[5 empty] | Estimate | 76 | 72 | 68 | 64 | 60 | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
[5 empty] | Actual | 76 | 75 | 75 | 66 | 66 | 65 | 61 | 61 | 61 | 61 | 61 | 61 | 61 | 56 | 56 | 56 | 56 | 47 | 47 | 47